## Hour by Hour Plan
Task ID | Date | Start Time | End Time | Task | Team | Reponsible | Preparation | Post-Check | Dependency | Status
T1 | 2019-01-28 | 16:00 | 16:30 | Get AWS account registed with build product manager and cloudtopus. | Infrastructure | Justin | Created AWS account | Google form submission succesful, and account added successfully on cloudtopus |  | completed
T2 | 2019-01-31 | 15:00 | 20:00 | Complete Hour-by-Hour plan and upload on e-learn | Infrastructure | Justin | Conducted team meeting and created Hour-by-Hour plan draft. | Hourd-by-Hour document successfully uploaded on elearn |  | completed
T3 | 2019-02-01 | 18:00 | 21:00 | Get AMI from product managers | Developers, Communications | Justin | 1. Product manager approval on Hour-by-Hour plan 2. Build 1.0.0 completed by developers and approved by QA. | AMI available under shared section on AWS EC2 dashboard | T1,T2 | completed
T4 | 2019-02-07 | 16:00 | 16:30 | Launch Deployment Environment Machine (EC2 instance) and configure security group (SSH) | Security | Ming Yu | SSH key pair generated using puttyGen | Upon Lauching the instance, clicking on view Instance shows the instance running. | T3 | Not started
T5 | 2019-02-07 | 16:30 | 17:00 | Enable connection via SSH and retrieve security credentials and public DNS of AWS EC2 instance. | Security | Ming Yu | Security groups successfully created on EC2 | Security keys successfully downloaded | T4 | Not started
T6 | 2019-02-07 | 17:00 | 17:15 | Test SSH connection via putty. | Security | Ming Yu | Security keys downloaded | Downloaded security keys able to establish connection to AWS EC2 instance successfully via putty using SSH | T5 | Not started
T7 | 2019-02-07 | 17:15 | 17:30 | Assign Elastic IP address and test connection | Infrastructure | Lingxing | AWS EC2 instance created | Deployment team able to connect to EC2 instance via elastic IP address | T6 | Not started
T8 | 2019-02-07 | 17:30 | 18:00 | Test build for business functionality - smoke test - Read-only-test - Functional and full test | Infrastructure | Lingxing | Product Manager and COO must be available to validate deployment success. | 1. The application functions and meets the required business ceriteria 1. All tests conducted on the application successful | T7 | Not started
Tests conducted
Smoke Test
1 | web search of http://13.229.2.90:8000/ returns successful http response |  |  |  | Success
2 | use server checker https://smallseotools.com/check-server-status/ to ensure that the deployed server is available to general public |  |  |  | Success (HTTP response: 200)
Read Only Test
1 | The SCP 1.0.0 build did not have any data available for us to perform read only tests |  |  |  | NA
Functional Test
1 | the index page loads as expected and the iframe link loads properly |  |  |  | Success
Full Test
1 | The application did not have any forms for input variables. Therefore, we ensured that the application is running and functioning |  |  |  | Success

## Teams
TEAMS
| PHONE | EMAIL
SECURITY
Ming Yu | 9888 0880 | mingyu.chua.2017@sis.smu.edu.sg
COMMUNICATIONS
Justin | 9321 9330 | justin.choy.2017@sis.smu.edu.sg
Tanny | 8533 8562 | tanny.lai.2017@sis.smu.edu.sg
QUALITY ASSURANCE
Hong Liang | 87798664 | hlng.2017@sis.smu.edu.sg
INFRASTRUCTURE
Keeve | 9658 6525 | keeve.quah.2017@business.smu.edu.sg
Lingxing | 9271 4836 | lxguo.2017@sis.smu.edu.sg
DEVELOPERS
Instructor Wendy | 6828 1967 | wendytanlc@smu.edu.sg
Instructor Michelle | 6828 9094 | michellekan@smu.edu.sg
DEPLOYMENT CHIEF OPERATIONS OFFICER
Professor Rafael | 6828 9675 | rafaelbarros@smu.edu.sg