## RACI
Change Management RACI Matrix for G5T5 Operations Team
Workflow Process | Immediate Team |  |  |  |  | Virtual Team
| Project Manager | Tier 1: Communications | Tier 2: Business Analyst | Tier 3: Development and Infrastructure | Security | Change Requestor | Business User
Acknowledge change request | I | R | I | I | I | A | -
Review/assess impact and risk of change request | A | I | R | I | C | - | -
Obtain approval for change | A | I | R | I | I | - | -
Implement required changes | A | I | I | R | C | - | -
Post-implementation regression testing | A | I | I | R | C | - | -
Resolve change request ticket | A | R | I | I | I | I | -
Notify Business User and conduct user satisfaction survey | A | R | C | I | I | - | I